## 01-SEP
CIRIL Daily Task Report — 01-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-01 | Tuesday | Understand the company’s business model and operational structure. | Completed company induction and leadership overview, and understood CIRIL’s nationwide operational presence and branch structure. | Building familiarity with the existing CRM workflow and data movement. | Detailed backend exposure | Took up onboarding, business-process understanding, and CRM workflow familiarization. | The CRM exposure established the foundation for subsequent backend analysis, database documentation, and Monitoring Portal workflow design.
|  | Learn the services offered by CIRIL, and understand lead generation and lead-handling workflow. | Learned the core services, lead-generation process, lead distribution, and lead-handling procedures, and understood the company’s share-distribution and royalty-allocation process. |  | Architectural workflow and flowchart design activities.
|  | Get familiar with the existing CIRIL CRM portal. | Received hands-on exposure to the existing CIRIL CRM portal and its operational workflow.

## 02-SEP
CIRIL Daily Task Report — 02-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-02 | Wednesday | Develop a working understanding of the CIRIL backend environment, CRM data arrangement and the underlying database structure. | Received authorised cPanel access with support from the Senior IT Analyst and reviewed the CRM data categories and database setup. | Initial backend familiarisation is complete, providing the base for the assigned technical tasks. | Prepare the first dummy-firm workflow flowchart using the findings from the backend and process study. | Task 1 assigned: research and design a complete workflow flowchart for a dummy firm. (Not Important, Priority: LESS, Irrelevant) | The Chairman sir introduced the Monitoring Portal concept for tracking tasks, deadlines and operational dues.
|  | Research flowchart standards, role relationships, decision stages and process movement before preparing the visual design. | Studied workflow symbols, role permissions, decision points and the sequence required to represent an operational process clearly. | Flowchart research is ongoing and is guiding the structure of the first workflow design. | Convert the research into a structured dummy-firm workflow draft for review. | Task 2 assigned: study Monitoring Portal workflow, technology options, pipelines and user-interface requirements.(Priority: HIGH) | The proposed portal requires role-based access, login/logout controls and location-based activity tracking.
|  | Prepare the approach for updating member passwords by zone and city code through a controlled local spreadsheet process. | Reviewed the required data handling approach and identified the information needed before processing can begin. | Work is pending receipt of the raw member spreadsheet from the authorised source. | Create and validate the local password-update workbook once the member data is provided. | Task 3 assigned: update member passwords using the prescribed zone and city-code convention. | This activity involves confidential credentials and member information and must follow secure handling procedures.

## 03-SEP
CIRIL Daily Task Report — 03-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-03 | Thursday | Plan the member password-update workbook and confirm an efficient, controlled processing method. | Reviewed the Excel procedures required for the task and received approval to use Python for the local processing activity. | The technical approach is ready; execution is awaiting the raw member data file. | Acquiral the authorised member data and begin the approved password-update process. | Additional requirement received: maintain separate GoDaddy and cPanel credential records for relevant members. | Password updating was identified as the immediate priority among the assigned deliverables.
|  | Map Monitoring Portal roles, responsibilities and access levels to support the workflow design. | Documented the key internal roles, including management, administration, business development and IT, along with their expected access responsibilities. | Role and access analysis is in progress for inclusion in the Monitoring Portal workflow. | Translate the role-based access rules into the detailed flowchart and system design. | Task 4 assigned: prepare DBMS portal user-friendly system guide with clear-cut instructions. | Chairman sir's, Admin and Manager roles require the ability to update every stage of an assigned task.
|  | Monitoring Portal: Identify a clear method for communicating a complex workflow to both technical and non-technical users. | Reviewed STAR, SIPOC, BPMN, CMMN and DMN methods to select useful approaches for process, decision and rule documentation. | The research is being consolidated into a practical workflow-documentation method. | Define scope, actors, process data, notation, validation steps and optimisation points for the final flowchart. | -- | The final documentation must allow a non-technical reader to understand the system workflow easily.

## 04-SEP
CIRIL Daily Task Report — 04-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-04 | Friday | Create a dependable reference for the CIRIL database and begin the supporting DBMS documentation. | Collected the existing schema architecture and SQL update instructions from the authorised CRM and DBMS environments. | Database documentation has been started using the extracted schema structure and related technical information. | Continue the DBMS and end-user guides after organising the initial database reference material. | End-user documentation was added alongside the assigned database-design documentation. | Access credentials were provided earlier for authorised work and continue to be treated as confidential.
|  | Convert the database structure into a reusable technical record that supports documentation and future analysis. | Created a JSON record covering entities, fields, engine details, charset, keys and constraints from the existing database design. | The JSON record now provides a structured base for the DBMS documentation work. | Extend the user guide from the login page through the remaining portal actions and workflows. | -- | The documentation is intended to cover both database design details and practical user actions.
|  | Define the Monitoring Portal architecture and the responsibilities of each user group within the system. | Established the roles of Admin, Manager and Employee, and organised the solution into Authentication, Management and Intelligence layers. | The overall portal architecture and role scope are defined and remain under detailed development. | Create the detailed decision based path switching workflow showing role-based hand-offs and system actions. | -- | The manager workflow now includes checking employee workload before assigning additional work.
|  | Improve the clarity of the Chairman Sir's-level workflow visual so it can be reviewed quickly without confusion. | Selected orthogonal lines and symmetrical columns to reduce crossing arrows and improve the readability of the process flow. | The high-level visual approach has been established and is ready for detailed diagram construction. | Complete the detailed workflow, exception paths and visual role separation. | -- | The final view will distinguish Admin oversight, Manager operations and Employee execution.

## 05-SEP
CIRIL Daily Task Report — 05-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-05 | Saturday | Monitoring Portal: Define the Intelligence and Analytical Layer so that operational activity can be converted into useful management information. | Defined Layer 3 as the part of the portal responsible for analytics, alerts, reports and organisational insights. | The purpose and scope of the Intelligence Layer are clearly defined for the next design stage. | Design the detailed data flow, reporting logic and dashboard presentation for this layer. | No new task was assigned during this activity. | The layer is intended to support management decisions rather than duplicate routine manager operations.
|  | Monitoring Portal: Identify the analysis functions required to monitor work delivery, workload balance and workforce activity. | Outlined modules for performance, workload, attendance, trends, patterns, exceptions and operational risks. | The core analytical modules are defined and ready for detailed functional design. | Specify the data inputs, business rules and expected outputs for each analytical module. | No new task was assigned during this activity. | The proposed analysis covers completion rates, overdue work, workload imbalance and recurring operational risks.
|  | Monitoring Portal: Plan how analytical results should be delivered to different roles through reports, alerts and dashboard views. | Conceptualised a central Insight Engine that combines task data, attendance data and user activity to generate actionable outputs. | The role-based reporting concept is progressing and requires detailed design specifications. | Design automated reports, alerts and dashboards for Admins, Managers and Employees. | No new task was assigned during this activity. | Predictive insights are marked as deprecated; the current focus is actionable analytics and automated reporting.

## 07-SEP
CIRIL Daily Task Report — 07-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-07 | Monday | Define employee availability statuses that reflect current work capacity within the Monitoring Portal. | Separated work availability from attendance and leave status to avoid mixing capacity information with HR records. | Availability rules have been drafted and will guide the employee workflow design. | Add the availability rules to the detailed employee workflow and supporting data model. | No new task was assigned during this activity. | Suggested capacity states include Available, Busy, On Break and In Meeting.
|  | Separate task lifecycle tracking from the record of work activity completed during each task. | Defined Task Execution as lifecycle management and Work Activity as the supporting record of actions taken during execution. | The distinction between lifecycle status and work activity has been documented for future design. | Design the workflow fields, controls and reporting rules for both records. | No new task was assigned during this activity. | Keeping the records separate will improve reporting accuracy and traceability.
|  | Monitoring Portal: Define the information employees should record while progressing an assigned task. | Outlined progress updates, work notes, time or effort entries and supporting evidence such as documents or screenshots. | The activity-recording concept is ready for detailed implementation design. | Specify the form fields, validation checks and storage approach for each work-activity entry. | No new task was assigned during this activity. | The record should capture both measurable effort and the context behind work or blockers.
|  | Monitoring Portal: Design an audit approach that preserves a reliable history of system changes and work activity. | Mapped separate audit histories for task state changes and for individual work-activity changes. | The dual-audit approach has been drafted for incorporation into the future architecture. | Define audit events, retention requirements and user access rules for audit information. | No new task was assigned during this activity. | Separate histories will make status changes and individual work actions easier to trace.
|  | Monitoring Portal: Finalise the Chairman sir's-level purpose of the Monitoring Portal flowchart and the expected management outputs. | Reconfirmed the Insight Engine and key analytical modules that convert operational data into reports, alerts and management insight. | The final flowchart objective has been documented and is ready for visual design. | Create the final flowchart showing roles, permissions, exception handling and management intelligence. | No new task was assigned during this activity. | The final visual should answer who uses the system, what they can do, how exceptions are handled and what management receives.

## 08-SEP
CIRIL Daily Task Report — 08-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-08 | Tuesday | Set up the local development environment and version-control workflow. | Installed and configured Git for local version control. Authenticated and configured the GitHub CLI (gh). Organized project-management workflows in GitHub Projects to support repository management and task tracking. | -- | -- | No new task was assigned during this activity. | Development environment setup was completed to support upcoming development work, repository management, and task tracking.
|  | Understand the LURE Holdings collaboration, business model, and brand requirements. | Attended the LURE Holdings x CIRIL strategy briefing and understood its seven business divisions, luxury positioning, and operational model. | UI design planning for the CIRIL DBMS Portal login page. | Completion and finalizing the UI design for the CIRIL DBMS portal | Assigned the CIRIL DBMS Portal Login Page UI design task. | --
|  | Begin UI planning for the CIRIL DBMS Portal login page and LURE x CIRIL landing page. | Began conceptual planning for the CIRIL DBMS Portal login-page UI and the LURE x CIRIL landing-page UI. | UI design planning for the LURE x CIRIL landing page. | Completion and finalizing the UI design for the CIRIL X LURE brand | Assigned the LURE X CIRIL landing-page UI design task. | The LURE X CIRIL designs must reflect the collobaration's luxury and exclusivity positioning.
|  | Resume the zonal password-configuration task. | Resumed processing spreadsheet data for the zonal password-configuration task, and noted chairman sir's requirments for the actual project | Zonal and city-code-based member password configuration. | Update the Monitoring Portal workflow and architecture to include employee-activity tracking, lead handling, and email operations. | Resumed the confidential zonal password-configuration task. | Chairman sir emphasized comprehensive employee-activity tracking as a core requirement the Monitoring Portal.
|  | Review Monitoring Portal requirements with the Chairman sir. |  | Integrating the expanded Monitoring Portal requirements into the system architecture. |  | Monitoring Portal scope was expanded to include the detail of employee activity tracking, lead handling flows, and email specifi operations.

## 09-SEP
CIRIL Daily Task Report — 09-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-09 | Wednesday | Design the LURE x CIRIL collaboration landing page. | Created 7 to 10 primary designs using Stitch for inspiration, laid out the foundational structure, and finalized two comprehensive UI design schemes utilizing engaging stock footage. | Applying minor changes and refinements to the primary web-pages. | Final approval and deployment of the LURE x CIRIL landing page designs. | -- | Completed two static web-page design of LURE X CIRIL. Awaiting presentation | q
|  | Finalize the zonal-based divisional password configuration. | Completed the initial setup for the zonal-based divisional password configuration. | Reconfiguring the passwords based on the reassignment instructions. | Complete the second iteration of the password reconfiguration. | Reassigned the task to reconfigure the password formats. | --

## 10-SEP
CIRIL Daily Task Report — 10-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-10 | Thrusday | Updated backend member passwords with secure hashing. | Manually updated the backend data by applying hashing to all member passwords for enhanced security. | Monitoring Portal: Workflow analysis. | Testing the newly hashed passwords to ensure proper system access, and functionality. | Assigned to sort out CRM's backend logic for allowing one user can access multiple location leads without disturbing the existing logic | The manual hashing process was completed successfully, secured the backend member credentials | q
|  | Finalize the front-end design of the LURE X CIRIL, UPDATE: CIRIL LUXENT, collabortion/promotion page | Updated the front-end design elements and successfully finalized the primary design file for the LURE X CIRIL (Update: CIRIL Luxent) page. | -- | -- | -- | The front-end file is now finalized and ready for next stage of updations regarding logo, and textual aspects.

## 11-SEP
CIRIL Daily Task Report — 11-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-11 | Friday | Test the newly configured and hashed member passwords for system functionality. | Tested each and every manually hashed passwords to verify login access and system functionality on validations. | Monitoring Portal: Workflow analysis. | Testing the newly hashed passwords to ensure proper system access, and functionality. | -- | All tested passwords are working completely fine without any login issues.
|  | Assigned with sorting out the CRM backend logic to allow a single user to access multiple location leads without disturbing the existing system logic. | Assessed the actual-internal architecture of the CRM to understand the current data flow and permissions. | Reviewing the entire backend PHP logic to identify the safest approach for implementing multi-location access. | Implement and test the new location access logic in the PHP backend | Logo to update the LURE X CIRIL is given, and awaiting the textual content to reconfigure the presentation. | The front-end file is now finalized and ready for next stage of updations regarding logo, and textual aspects.

## 15-SEP
CIRIL Daily Task Report — 15-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-15 | Tuesday | Monitoring Portal: Update the primary employee workflow, and design employee workflow issues tracking and coordinating system. | Came up with Ticket issue tracking system, coordinating the with the higher authority under few level of severities. | Monitoring Portal: Assessing the intelligence-analytical layer, with automated report generators under different scenarios. | Still designing the proper system-architecture of the Internal CRM i. e Monitoring Portal. | -- | --
|  | CIRIL-LUXENT, need to update the design of the landing or introduction page | Re-assessed stock footage, and reconfigured the text that need to be updated, and need to re-design the layout of the page. | Stock-footages need to be color graded and edited to update the dynamic view of the page. | Logo: CIRIL-LUXENT is awaited, and complete update of the actual page. | -- | --

## 16-SEP
CIRIL Daily Task Report — 16-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-16 | Wednesday | Monitoring Portal: Need to work on creating user-specific task tracking metrics. | Re-assessed the Internal operations tracking system's involving character's metrics on overview basis. As specified by Chairman sir's added 4 levels of manager for the actual system access, and re-mapped all the privileges regarding the different level of roles, and their perspectives. | Monitoring Portal (Internal Operations Tracking System): Need to work on clear-cut of employee based task metrics to track each employee key performance. | CIRIL-LUXENT UI designing is still pending, and need to reconfigure the textual content of the page. | Assigned to recover the lost data in flash-drive. | --
|  | Task is to recover the lost files on the specific pendrive. | Task is completely completed, and remain successful on recovering the lost data successfully. | Compression of the recovered data is in progress. |  | Assigned to find ChatGPT business plans, and report to it higher authorities. | --

## 17-SEP
CIRIL Daily Task Report — 17-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-17 | Thursday | Monitoring Portal: Need to work on clear-cut employee based task metrics to track each employee key performance. | As per the reassessment yesterday, the employee specific metric, overview descriptive analysis is prepared. | Monitoring Portal (Internal Operations Tracking System): Based on the prepared metrics, rough UI dashboards that are completely for reference is in progress. | CIRIL-LUXENT UI designing is still pending, and need to reconfigure the textual content of the page. | -- | --
|  | Compress all the large recovered files in flash-drive, and need to work on finding details regarding the ChatGPT business plans. | Compressed all the required files and handed over the flash-drive to respective person, and assessed the ChatGPT business plans and followed up the details to the higher authority. |  |  | -- | --

## 18-SEP
CIRIL Daily Task Report — 18-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-18 | Friday | Monitoring Portal: Gathered dashboard design requirements, in system - operational level. | Laid out dashboard designs requirements, and mapped the foundational functional and non-functional requirements. | Laying out and configuring the dashboards for maintaing the internal system connections so the data flow is efficient, load balancing needs to be mapped out, for system strength in handling complete heavy burden. | Remap the entire Internal Operations Tracking System flow strictly from a data flow perspective. | -- | --
|  | Prepare and configure a list of codex-tools that would completely assist in firm's purchase of ChatGPT - Codex's performance with less token burning. | Completed the research on different kinds of plugins that assists ChatGPT-Codex's performance to perform fast, as they are essential in the project that has been assigned to me. | Laying out and configuring the required plugins for the upcoming codex tools. | Looking into other tools that widely increase the working of Coding - Agent. | -- | Extensive research on codex optimization was prioritized to guarantee a premium output for the upcoming modular development phases.

## 19-SEP
CIRIL Daily Task Report — 19-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-19 | Saturday | Finalized the CIRIL-LUXENT frontend of the landing page design. | Updated the CIRIL-LUXENT logo and designed the complete frontend based on the data received from Rishabh Sir. | Internal Operations Tracking System, entire technical architecture mapping. | Awaiting discussion with Rishabh Sir for final approval due to limitations on the logo design and theme match. | -- | Frontend Design is complete but on hold pending final theme to match up the logo approval from Rishabh sir.
|  | Acquire, verify, and study the backend access for Ciril. in and Officespace. ciril. in for in-house maintenance. | Tested the provided credentials for cPanel, and FTP, and GoDaddy | Troubleshooting server access issues as the credentials provided are failing to authenticate, and in progress found that user accounts are changed completely by creds to GoDaddy creds given by Manasa ma'am. | Contact Bitra Group to acquire valid hosting credentials. | Assigned to take over the backend maintenance architecture for Ciril. in and Officespace. ciril. in. | Maintainance takeover is temporarily blocked until Bitra Group provides the correct access details.

## 21-SEP
CIRIL Daily Task Report — 21-SEP-2026
Daily work summary report
IOTS: Internal Operations Tracking System
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-21 | Monday | CIRIL-LUXENT review, and approval. | CIRIL LUXENT site completely refined regarding the UI animations, and all kind of hovering effects. Designed an extended carousel effect so that it would look premium and elevate the branding of the brand. | Awaiting approval and need to make few more textual tweaks, and waiting for a video. | -- | -- | --
|  | IOTS: Need to logically design the underlying system architecture for the Authentication and Authorization layer. | Primary design and layout for the Employee based login UI page, with extensive animations making it look premium. Constructed the Authentication and Authorization module for the IOTS. Configured the underlying configuration of Oauth, API Calls, and required technology stack for encrypted authetication. | Design for the backend logic, RBAC, Location Validation, User Auth to Server, API Calls need to be laid out. | -- | DBMS Portal, raised a bug on importing listings data via excel import. (Resolution is need to be done ASAP) | Upon again in discussion with Chairman Sir, he also insisted to include rewarding system for employee monthly, and quaterly etc.
|  | Assigned with troubleshooting the DBMS portal excel sheet import mis-functionality | Listing data imported from excel in DBMS portal, raised critical image mispositions, and it is resolved under local host. | This internal bug caused operational instability for Trinity Partners, and bug is solved and need to be updated on live server | -- | --

## 22-SEP
CIRIL Daily Task Report — 22-SEP-2026
Daily work summary report
IOTS: Internal Operations Tracking System
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-22 | Tuesday | Finalize CIRIL-LUXENT landing page tweaks and integrate video. | Applied the final textual tweak to the frontend UI as requested. | Integrating the final video asset to the CIRIL-LUXENT page. | Awaiting for the final-video to integrate into the CIRIL-LUXENT Page. | -- | Frontend is fully refined; ready for deployement once the video is finalized and approved.
|  | Design IOTS authentication backend logic for RBAC, API calls, and adding additional draft on employee rewarding system. | Laid out the core backend logic for Role Based Access Control (RBAC), Location validation and User Authentication to Server. | Structuring the server API calls and mapping out the montly/quaterly employee rewarding system as specified by chairman sir. | Finalize the parameters and metrics for the rewarding system with management. | Conceputalize the logic and database structure for the monthly and quaterly employee reward system. | --
|  | Deploy the DBMS Portal's Excel import bug fix to the live server. | Successfully deployed the local-host fix for the Excel import functionality (image misposition bug) to the live server. | Monitoring the LIVE DBMS portal to ensure operational stability. | -- | -- | The critical bug has been fully resolved on the live server, and listing data import are functioning correctly.

## 23-SEP
CIRIL Daily Task Report — 23-SEP-2026
Daily work summary report
IOTS: Internal Operations Tracking System
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-23 | Wednesday | Configure the development environment and design the IOTS login page's UI. | Successfully configured Google's Antigravity CLI for the development environment. | Reviewing and assessing multiple design styles and themes for the IOTS login page. | -- | -- | Successfully configured the AntiGravity CLI for the development environment and working extensively on mapping the backend tech for RBAC system design in the sense of internal operations.

## 24-SEP
CIRIL Daily Task Report — 24-SEP-2026
Daily work summary report
IOTS: Internal Operations Tracking System
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-24 | Thursday | Finalized the UI design system and login page layout for the IOTS. | Continued reviewing and refining the UI design styles for the IOTS login page to establish a well-designed system. | Developing the actual frontend layout based on the selected design theme. | Complete the login page frontend coding and connect it to the local-host's authentication backend logic. | -- | Dedicated additional time to ensure the foundational design language (CSS, React-JS, Themes, Animations) is perfectly set, which will speed up the development of all subsequent portal dashboards.
|  | Analyze and Review the backend architecture of CirilCrm.net's: ciril.in, and officespace.ciri.in. | Began reviewing the existing backend structure and server environment for the mentioned websites. | Familiarizing myself with the legacy backend code and database relationships for ciril.in and officespace.ciril.in | Completely understood and reviewed the entire backend logic and can perform updates directly from our end, with few more research assessment. | -- | --

## 26-SEP
CIRIL Daily Task Report — 26-SEP-2026
Daily work summary report
IOTS: Internal Operations Tracking System
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-26 | Saturday | Finalize IOTS login functionality, integrate location tracking telemetry, and develop frontend test cases. | Finalized the React-based login interface with Dark/Light mode support and a WebGL animated background. Integrated high-precision live GPS telemetry with reverse geocoding to fetch exact coordinates and locality. Built a location permission security gate that strictly restricts access if telemetry is denied. Developed a Testing Scenarios dock to run frontend test cases for 'Success', 'Failed', and 'Mismatch' login states | Connecting the finalized frontend telemetry and login states to the actual backend authentication API. | Final end-to-end integration testing with the live backend server. | -- | The frontend functionality is complete, and the location tracking rigorously enforces the enterprise access protocol by visually detailing GPS locks and mismatches.

## 28-SEP
CIRIL Daily Task Report — 28-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-28 | Monday | Compile technical documentation, optimize the IOTS frontend codebase, and secure design approval. | Received official frontend design approval for the login page from Chairman Sir. Authored a complete architectural document for the portal and executed a final code cleanup to ensure 100% code balance. | Preparing the fully documented and approved frontend for backend API integration. | Connect the documented authentication states and location mismatches to the live backend server. | -- | Chairman Sir's design approval and the comprehensive documentation provide a strict, authorized blueprint for the upcoming backend integration phase.

## 29-SEP
CIRIL Daily Task Report — 29-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-29 | Tuesday | Configure API authentication, establish live Node server connection, and restructure React UI components. | Restructured the frontend codebase by dividing the React UI components into a modular app structure. | Reconfiguring the API authentication logic and troubleshooting the environment on the live Node server. | Finalize the API authentication logic and complete end-to-end testing against the live server. | Assigned to assist Praneeth with the CRM negotiations Kanban UI. | The React UI is successfully modularized, but the API authentication logic requires further reconfiguration before it is fully functional on the live server.
|  | Need to configure the issue with the Kanban summary pop-up window for the CRM's negotiations pane of the Lead's. | Collaborated with Praneeth to build and finalize the Kanban summary pop-up window pane; verified it is fully working and functional based on required metrics. | -- | -- | -- | The pop-up window is fully functional and successfully meets the operational metrics required for the negotiations pane.

## 30-SEP
CIRIL Daily Task Report – 30-SEP-2026
Daily work summary report
Date | Day | Tasks to be done | Task Completed | Tasks in Progress | Tasks pending | Any new tasks assigned or taken up during the day | Remarks
2026-09-30 | Wednesday | Unify disparate operational documentation (claude_version.docx and gemini_version.docx) into an official, single technical documentation file for IOTS. | Synthesized comprehensive official documentation covering system architecture, organizational role mappings (Executive to Chairman), and CIRIL commercial equations (30/70 split, 7.5% royalty, 100-point performance scoring). | -- | -- | Extracted and standardized CIRIL operational logic and role definitions from source documents into official project documentation. | Official documentation is finalized in a unified file, serving as the master architectural reference for development.
|  | Design, generate, and validate an enterprise-grade Draw.io flowchart based on Actual-FlowChart.drawio and role-specific requirements. | Built and generated new_updated_flowchart_2.drawio containing 9 dedicated pages (Master Architecture + 8 Role-Specific views). Resolved XML schema geometry bugs (as="geometry") across 389 tags and eliminated arrow overlaps using corridor-based activity buses. | Flowchart structure and multi-perspective analytical data flow are under review and assessment before architectural baseline freeze. | Stakeholder assessment and final sign-off on the 9-page flowchart architecture to proceed with UI workflow implementation. | Separated architecture into role-specific sub-pages, mapped central data-logging to intelligence perspectives, and converted technical jargon to plain business English. | The multi-page Draw.io flowchart is fully generated and verified for XML compliance; pending leadership assessment and feedback.