## Oct-1
DATE | DAY | TASKS TO BE DONE | TASKS COMPLETED | TASK IN PROGRESS | TASK PENDING | ANY NEW TASKS ASSIGNED OR TAKEN UP DURING THE DAY | REMARKS
01-10-2026 | Thursday | Define IOTS user roles, access limits, and design documentation. | Documented roles and responsibilities across Admin, management, regional, and member-office work. | Preparing the role-based access matrix and rules for higher-level permissions. | Designing the role-based dashboards, and defining other indepth metrics | Started mapping system access levels to user roles.
|  | Review CIRIL-CRM backend code, database structure. | Reviewed the backend code and identified permission rules, lead workflows, and session limits. | Tracing how Super Admin doesn't have privilage to change the member-office lead ownership. | Need to work on programming logic behind the super-admin privilage to edit lead of a member company, under it's prospect status.

## Oct-3
DATE | DAY | TASKS TO BE DONE | TASKS COMPLETED | TASK IN PROGRESS | TASK PENDING | ANY NEW TASKS ASSIGNED OR TAKEN UP DURING THE DAY | REMARKS
03-10-2026 | Saturday | Create role-based workflow diagrams and draft dashboard layouts for IOTS. | Created the first workflow diagrams and dashboard layout sketches for different roles. | Refining decision points and improving the dashboard layouts. | Finalize screen layouts and role-specific metrics. | Started simplifying the Admin workflow. | Some approval steps need clearer paths. Dashboard design is underway.
|  | Review why Super Admin lead-edit access was restricted and fix controls. | Fixed the issue locally where lead-edit buttons appears for users who have created a particular lead, and tested Super Admin access, and edit privilege. | Testing the related CRM changes and checking less common cases. | Test the changes in staging and complete the code review. |  | Local testing confirms the controls now appear only for users with the correct access. Need to reflect it on the server.

## Oct-5
DATE | DAY | TASKS TO BE DONE | TASKS COMPLETED | TASK IN PROGRESS | TASK PENDING | ANY NEW TASKS ASSIGNED OR TAKEN UP DURING THE DAY | REMARKS
05-10-2026 | Monday | Refine Super Admin lead-edit access and document the code changes. | Updated the local Super Admin lead-edit logic and documented the affected files and code sections. | Checking that lead updates do not change other data by mistake. | Complete peer review and submit the code changes for approval. | Created a change log listing the affected files and code sections.
|  | Prepare draft dashboard layouts for each role in the current specification. | Created draft dashboards for Super Admin, Executive, Manager, Member Officer, and Field Agent. | Making layouts, metrics, and action triggers are consistent across the dashboards.

## Oct-6
DATE | DATE | DAY | TASKS TO BE DONE | TASKS COMPLETED | TASK IN PROGRESS | TASK PENDING | ANY NEW TASKS ASSIGNED OR TAKEN UP DURING THE DAY | REMARKS
06-10-2026 | Tuesday | Design the IOTS login process and set up a clear, layered backend structure. | Designed the authentication flow and separated the backend into controllers, services, and repositories. | Working on session renewal, login request limits, and role-based access checks. | Add shared error handling and audit records for important login and security events. |  | The modular structure will be easier to test and extend.
|  | Review the full system workflow and update role-based IOTS requirements. | Reviewed the system workflow and updated the requirements for tracking work across roles. | Turning the findings into clear development tasks and API requirements for location tracking. | Review security risks when users have access to more than one role. |  | The review helped identify workflow gaps and clarify how they should be handled.

## Oct-7
DATE | DATE | DAY | TASKS TO BE DONE | TASKS COMPLETED | TASK IN PROGRESS | TASK PENDING | ANY NEW TASKS ASSIGNED OR TAKEN UP DURING THE DAY | REMARKS
07-10-2026 | Wednesday | Map workflows for all roles and include the proposed reward system. | Updated the workflows to reflect role responsibilities and added the proposed weekly, monthly, and quarterly rewards. | Working on the scoring rules and performance measures for rewards. | Define how reward records and performance history will be stored. | Added a draft structure for weekly, monthly, and quarterly rewards. | The reward process is included in the workflow; scoring rules still need to be finalized.
|  | Update the IOTS technical design and review the requested change to the CRM lead-edit time limit. | Updated the IOTS design documents and reviewed the requested change to the CRM lead-edit time limit. | Defining role-specific performance measures and tracking formulas. | Update the time limit in the CIRIL-CRM lead-edit code. | Started defining performance measures for individual team members. | The existing 15-minute lead-edit limit was identified for review.

## Oct-8
DATE | DAY | TASKS TO BE DONE | TASKS COMPLETED | TASK IN PROGRESS | TASK PENDING | ANY NEW TASKS ASSIGNED OR TAKEN UP DURING THE DAY | REMARKS
08-10-2026 | Thursday | Change the CRM lead-edit time limit from 15 minutes to 48 hours and design a Super Admin edit-request process that keeps the original member office as owner. | Changed the time limit to 48 hours locally and drafted the Super Admin edit-request process without changing lead ownership. | Building the edit logic so changes update the existing lead without changing its source or owner. | Test the full process, from the member office request to the Super Admin update. | Priority: allow member offices to request lead changes at any time, while keeping the existing lead record. | The time limit has been changed locally. The new process is designed to preserve lead ownership and history.
|  | Update IOTS analytics requirements and help set up design tools on the workstation. | Updated the IOTS analytics setup to capture missing activity and audit records. Installed Photoshop and Illustrator on Harshitha's PC. | Tuning data summaries and historical trend calculations for IOTS reports. | Check that design files move correctly from the workstation into the IOTS frontend asset library. | Completed workstation setup support for the creative tools. | Analytics coverage has been expanded, and the workstation is ready for design work.

## Oct-9
DATE | DAY | TASKS TO BE DONE | TASKS COMPLETED | TASK IN PROGRESS | TASK PENDING | ANY NEW TASKS ASSIGNED OR TAKEN UP DURING THE DAY | REMARKS
2026-09-10 | Friday | Review the IOTS flowchart and identify any missing enterprise-level functions. | Reviewed the existing architecture and identified additional functions, including approval workflows, document management, search, scheduling, integrations, data governance, security, and system recovery. | Reviewing how these shared functions can fit into the existing architecture without making the flowchart too complex. | Finalize the required additions and update the master flowchart. | Add a shared enterprise services section covering common system functions. | The existing flowchart covers the main operational workflows well. The proposed additions will make the overall architecture more complete.

## Oct-12
DATE | DAY | TASKS TO BE DONE | TASKS COMPLETED | TASK IN PROGRESS | TASK PENDING | ANY NEW TASKS ASSIGNED OR TAKEN UP DURING THE DAY | REMARKS
2026-12-10 | Monday | Update the Github's progress, and upload the complete system based configured, Complete the backend logic for the authentication, and design of the database of the IOTS system | Completely updated the Github's progress, and uploaded the complete system based architecture. | Still require in depth testing for the backend logic for authentication system for IOTS system, and database design configuration is still in progress. | Finalize the testing of authentication the backend.